## Projects
ProjectID | ProjectName | ProjectManager | StartDate | Deadline | Budget | Priority | ProjectStatus
P001 | Website Redesign | Arun Kumar | 2026-08-01 | 2026-11-30 | 250000 | High | In Progress
P002 | Mobile App Development | Priya Sharma | 2026-07-15 | 2026-12-15 | 500000 | High | In Progress
P003 | Customer Analytics | Rahul Verma | 2026-08-20 | 2026-10-31 | 180000 | Medium | In Progress
P004 | Inventory Automation | Divya Nair | 2026-06-01 | 2026-09-25 | 300000 | High | At Risk
P005 | Employee Portal | Arun Kumar | 2026-09-01 | 2026-12-20 | 220000 | Medium | Not Started

## Tasks
TaskID | ProjectID | TaskName | AssigneeID | Priority | StartDate | DueDate | ProgressPct | Status | PlannedDurationDays | ActualDurationDays
T001 | P001 | Design homepage | E001 | High | 2026-08-03 | 2026-08-12 | 100 | Completed | 5 | 5
T002 | P001 | Create wireframes | E002 | High | 2026-08-04 | 2026-08-14 | 100 | Completed | 7 | 7
T003 | P001 | Build responsive layout | E003 | High | 2026-08-15 | 2026-09-10 | 80 | In Progress | 12 | 10
T004 | P001 | Integrate contact form | E004 | Medium | 2026-09-01 | 2026-09-18 | 60 | In Progress | 6 | 4
T005 | P001 | Website testing | E005 | Medium | 2026-09-19 | 2026-10-05 | 0 | Not Started | 5 | 0
T006 | P002 | Gather app requirements | E006 | High | 2026-07-16 | 2026-07-30 | 100 | Completed | 8 | 8
T007 | P002 | Design app UI | E002 | High | 2026-08-01 | 2026-08-20 | 100 | Completed | 10 | 10
T008 | P002 | Develop login module | E003 | High | 2026-08-21 | 2026-09-15 | 75 | In Progress | 15 | 12
T009 | P002 | Build booking feature | E007 | High | 2026-09-01 | 2026-10-10 | 45 | In Progress | 20 | 9
T010 | P002 | Perform app testing | E005 | Medium | 2026-10-11 | 2026-11-05 | 0 | Not Started | 10 | 0
T011 | P003 | Collect source data | E006 | Medium | 2026-08-21 | 2026-08-30 | 100 | Completed | 5 | 5
T012 | P003 | Clean dataset | E001 | Medium | 2026-08-31 | 2026-09-10 | 100 | Completed | 6 | 6
T013 | P003 | Create Power BI model | E004 | High | 2026-09-11 | 2026-09-25 | 70 | In Progress | 8 | 6
T014 | P003 | Build KPI visuals | E007 | Medium | 2026-09-26 | 2026-10-08 | 30 | In Progress | 7 | 2
T015 | P003 | Validate dashboard | E005 | Low | 2026-10-09 | 2026-10-20 | 0 | Not Started | 5 | 0
T016 | P004 | Map current workflow | E006 | High | 2026-06-02 | 2026-06-12 | 100 | Completed | 7 | 7
T017 | P004 | Configure inventory database | E003 | High | 2026-06-13 | 2026-07-10 | 100 | Completed | 18 | 18
T018 | P004 | Develop stock alerts | E004 | High | 2026-07-11 | 2026-08-05 | 100 | Completed | 12 | 13
T019 | P004 | Integrate barcode scanner | E007 | High | 2026-08-06 | 2026-08-28 | 80 | In Progress | 10 | 14
T020 | P004 | User acceptance testing | E005 | Medium | 2026-08-29 | 2026-09-20 | 50 | In Progress | 8 | 5
T021 | P005 | Define portal requirements | E001 | Medium | 2026-09-02 | 2026-09-12 | 100 | Completed | 6 | 6
T022 | P005 | Create portal prototype | E002 | Medium | 2026-09-13 | 2026-09-30 | 40 | In Progress | 8 | 3
T023 | P005 | Develop employee directory | E003 | Medium | 2026-10-01 | 2026-10-25 | 0 | Not Started | 12 | 0
T024 | P005 | Add leave request module | E004 | Low | 2026-10-10 | 2026-11-15 | 0 | Not Started | 14 | 0
T025 | P005 | Conduct security review | E005 | High | 2026-11-16 | 2026-12-05 | 0 | Not Started | 7 | 0

## Team
EmployeeID | EmployeeName | Department | Role
E001 | Asha Menon | Design | UI Designer
E002 | Karthik Raj | Design | UX Designer
E003 | Meera Iyer | Development | Developer
E004 | Vikram Singh | Development | Developer
E005 | Sneha Patel | Quality Assurance | QA Analyst
E006 | Imran Khan | Analytics | Data Analyst
E007 | Neha Reddy | Development | Developer